## Product Backlog
| Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone1 | Milestone1 |  | Choose the data,Read the data file,Store data in the database and fetch data, Do text cleaning and normalization using multiprocessing | MUST HAVE | - | K.Nancy Grace | 3- Completed
Milestone2 | Milestone2 |  | Email sending,Count Vectorizer,Sentiment Analysis,store data in db,parallelsim,Sending summary email | MUST HAVE | - | K.Nancy Grace | 3- Completed
Milestone3 | Milestone3 |  | Load dataset,LLM or Unsupervised learning algorithm,Save results in CSV, measure accuracy and performance | MUST HAVE | - | K.Nancy Grace | 3- Completed
Milestone4 | Milestone4 |  | UI part for the project | MUST HAVE | - | K.Nancy Grace | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Milestone1 | 1 | Choose data and store in database,normalization and mulitiprocessing | 16-09-2025 | 17-09-2025 | K.Nancy Grace | Coding | 3- Completed | 2
Milestone2 | 2 | Count Vectorizer,Sentiment analysis,store data,parallelism,summary email | 30-09-2025 | 2025-01-10 | K.Nancy Grace | Coding | 3- Completed | 6
Milestone3 | 3 | Load Dataset,LLM,Saves results in csv,mail the csv file,measure the accuracy and performane | 2025-10-10 | 13-10-2025 | K.Nancy Grace | Coding | 3- Completed | 6
Milestone4 | 4 | UI part for the project | 17-10-25 | 23-10-2025 | k.Nancy Grace | Design | 3- Completed | 3

## Stand up Meeting
| Day | Impediments | Action Taken
1 | 2025-08-09 | Overview of the project | learned about text processing
1 | 2025-09-09 | Sequential processing vs Parallel processing | understood working of code
1 | 2025-10-09 | sqlite3 in database | worked with database sqlite3
1 | 2025-11-09 | regular expression concepts | learned about regex topics
1 | 2025-12-09 | dataset selection | loaded the dataset
1 | 15/9//2025 | dataset storing in database | stored the data in the database
1 | 16/9/2025 | multiprocessing techniques | applied multiprocessing
1 | 17/09/2025 | milestone1 presentations | presented the milestone 1
2 | 18/9/2025 | problem statements(sentiment analysis,topic modelling | understood the problem statements
2 | 24/9/2025 | email sending | worked on email libraries
2 | 26/9/2025 | problem statement(final) | i chosed sentiment analysis
2 | 30/9/2025 | parallel text data in llm | preprocessed data to string
2 | 2025-01-10 | llm implementation | trained llms
2 | 2025-03-10 | stored results in database | stored results in database
2 | 2025-04-10 | milestone2 presentations | presented the milestone 2
3 | 2025-06-10 | performance mettrices | searched about performance metrices
3 | 2025-09-10 | traditional method (performance) | implementation of code
3 | 2025-10-10 | time comparison concepts | performance time btw sequential vs parallel processing
3 | 2025-11-10 | llm or unsupervisied algorithm | implemented using best unsupervised algorithm
3 | 13/10/2025 | performace of sentiment analysis | performance metrices for sentimetn analysis
3 | 14/10/2025 | best model among traditional and modern methods | completed the work of modern method
3 | 15/10/2025 | milestone 3 presentations | presented the work
3 | 16/10/2025 | streamlit library | learned about streamlit
4 | 17/10/2025 | explained milestone 4 tasts | build the streamlit app for my project
4 | 23/10/2025 | build login page for the project | created login page
4 | 24/10/2025 | added navigation bar | added navigation radio buttons
4 | 27/10/2025 | comparsion between 2 methods | compared the methods
4 | 30/10/2025 | email summary | sent email summary
4 | 2025-03-11 | ppt presentations | working on ppt

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 16-09-2025 | 17-09-2025 | K.Nancy Grace | Selecting and loading datasets | Parallel processing | - | No
2 | 2 | 30-09-2025 | 2025-01-10 | K.Nancy Grace | Automating reports and testing regularly | Result verification | - | No
3 | 3 | 2025-09-10 | 13-10-2025 | K.Nancy Grace | Modern method vs Traditional method | Spending more time on the data | - | No
4 | 4 | 17-10-2025 | 24-10-2025 | K.Nancy Grace | Started designing UI using streamlit | Done with testing part | Working on ppt | No